## PROJECT CARGO
| LOADING POINT | PORT
| COMMODITY | VARIOUS - 6 X LINKS -2604DSI2804-BA3188
| OFFLOADING POINT | KAMOTO
TRACKING REPORT
NO. | LOADING PLACE | DESTINATION | HORSE | TRAILER 1 | TRAILER 2 | DRIVER NAME | PASSPORT | ETA AT LOADING POINT | DATE ARRIVED | DATE LOADED | DATE DISPATCHED | GRB |  | KAZUNGULA/CHIRUNDU |  | KASUMBALESA/ MOKAMBO |  | WHISKEY |  | OFFLOADING POINT |  | CURRENT POSITION | STATUS
[12 empty] | Arrival Date | Departure Date | Arrival Date | Departure Date | Arrival Date | Departure Date | Arrival Date | Departure Date | Arrival Date | Offload Date
1 | PORT | KAMOTO | KB12WBGP | DR24FYGP | DR24FSGP | TAFADZWA MBANO | AE735649 | 2026-06-01 | 2026-05-30 | 2026-06-01 | 2026-06-02 | 2026-06-04 | 2026-06-07 | 2026-06-09 | 2026-06-11 | 2026-06-13 | 2026-06-14 | 2026-06-14 | 2026-06-17 | 2026-06-20 |  | KOLWEZI KCC | WAITING TO OFFLOAD
2 | PORT | KAMOTO | LH12PDGP | MH38RRGP | MH38RXGP | GODWIN MANHIKA | BE042905 | 2026-06-01 | 2026-05-30 | 2026-06-01 | 2026-06-02 | 2026-06-04 | 2026-06-06 | 2026-06-09 | 2026-06-11 | 2026-06-13 | 2026-06-14 | 2026-06-14 | 2026-06-17 | 2026-06-20 |  | KOLWEZI KCC | WAITING TO OFFLOAD
3 | PORT | KAMOTO | LF88XTGP | LV01GLGP | LV01HKGP | RUTENDO SHEPHARD DHLORA | BE878505 | 2026-06-01 | 2026-05-30 | 2026-06-01 | 2026-06-02 | 2026-06-04 | 2026-06-06 | 2026-06-09 | 2026-06-11 | 2026-06-13 | 2026-06-14 | 2026-06-14 | 2026-06-17 |  |  | LIKASI | IN TRANSIT
5 | PORT | KAMOTO | HN26CNGP | BW54XPGP | BW54XJGP | FLETCHER THEMBI PHIRI | GN482335 | 2026-06-01 | 2026-05-30 | 2026-06-01 | 2026-06-02 | 2026-06-05 | 2026-06-06 | 2026-06-08 | 2026-06-10 | 2026-06-12 | 2026-06-14 | 2026-06-14 | 2026-06-17 |  |  | LUKUNI LUBUMBASHI | IN TRANSIT
4 | PORT | KAMOTO | KC14XXGP | KT40MVGP | KT40MYGP | JOYCE TARIRO MURAURO | AE852674 | 2026-06-01 | 2026-05-30 | 2026-06-01 | 2026-06-02 | 2026-06-04 | 2026-06-06 | 2026-06-09 | 2026-06-11 | 2026-06-13 | 2026-06-14 | 2026-06-14 | 2026-06-17 |  |  | TENKE FUNGURUME | IN TRANSIT
6 | PORT | KAMOTO | KT12NBGP | FS77HKGP | FS77HWGP | DENGU, WILFANOS | BE180651 | 2026-06-01 | 2026-05-30 | 2026-05-31 | 2026-06-01 | 2026-06-05 | 2026-06-07 | 2026-06-09 | 2026-06-11 | 2026-06-13 | 2026-06-14 | 2026-06-14 | 2026-06-17 |  |  | LUMATA | IN TRANSIT