## Lufu shipment (hidden)
D25238- PROJECTS
[8 empty] | TRACKING REPORT - | OK AFRICA
NO | TPT | FORWARDER | TRUCK NUMBER | TRAILER 1 | TRAILER 2 | CAPACITY | REF | DRIVERS NAME | ID/PASSPORT NUMBER | ARRIVAL DATE | LOADING DATE | DISPATCH DATE | ARR RAMA | DES RAMATLA | ARR MAMUNO | DES MAMUNO | ARRIV Oshikango | ARRIVAL Santa Clara | ARRIVAL Lufu | DISPATCH Lufu | ARRIVAL AT OFFLOADING | OFFLOADING DATE | CURRENT LOCATION | CURRENT STATUS | EXIT POINT | ENTRY POINT | LOADING POINT | DELIVERY POINT | Tris File No.
1 | UNACENTIA HOLDINGS | POLYTRA | LZ27WFGP | KZY488NW | N/A | 34T |  | WEMMICK TUMS | AE993986 | 2025-08-28 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-08-31 | 2025-09-01 | 2025-09-01 | 2025-09-01 | 2025-09-08 | 15/09/2025 | 15/09/2025 | Lufu DRC | Lufu Border DRC Side | offloaded

## BA3195
LOADING POINT | DURBAN PORT
COMMODITY | PROJECT CARGO
OFFLOADING POINT | FRONTIER
ORIENTO TRACKING REPORT
NO | file | TPT | FORWARDER | TRUCK NUMBER | TRAILER 1 | TRAILER 2 | CAPACITY | REF | DRIVERS NAME | ID/PASSPORT NUMBER | ARRIVAL DATE | LOADING DATE | DISPATCH DATE | ARR GRB / BBR | DES GRB / BBR | ARR KAS / CHIRUNDU | DES KAZ / CHIRUND | ARRIV SAK ZAM | ARRIVAL SAK DRC | ARRIVAL WHISKEY | DISPATCH WHISKEY | ARRIVAL AT OFFLOADING | OFFLOADING DATE | CURRENT LOCATION | CURRENT STATUS | EXIT POINT | ENTRY POINT | LOADING POINT | DELIVERY POINT | Tris File No.
1 | BA3195 | TIGER ZAMBEZI | ORIENTO | BCJ1887ZM | BCF1830ZM | BCF1831ZM | 34 |  | EZIRON MUSHIKA | ZN859716 | 2026-05-30 | 2026-06-02 | 2026-06-02 | 2026-06-03 | 2026-06-14 | 2026-06-15 | [7 empty] | KAZUNGULA | WAITING TO CROSS | GRB | KASUMBALESA | DURBAN PORT | FRONTIER
2 | BA3195 | TIGER ZAMBEZI | ORIENTO | CAL8238ZM | ETF754GP | N/A | 30 |  | BAGREY SIMOOBA | ZP103728 | 2026-05-30 | 2026-06-02 | 2026-06-02 | 2026-06-03 | 2026-06-14 | 2026-06-15 | [7 empty] | KAZUNGULA | WAITING TO CROSS | GRB | KASUMBALESA | DURBAN PORT | FRONTIER
3 | BA3195 | ELMAN | ORIENTO | BCF8689ZM | BCF5929ZM | BCF5930ZM | 34 |  | DAVIES NYIRONGO | ZN904300 | 2026-05-31 | 2026-06-02 | 2026-06-02 | 2026-06-04 | 2026-06-14 | 2026-06-16 | [7 empty] | KAZUNGULA BORDER | UNDER CLEARANCE | GRB | KASUMBALESA | DURBAN PORT | FRONTIER